## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Dask and parallel Processing | MUST HAVE | No Dependency | Gogula Avinash | 3- Completed
S2 | S2 | US-001 | Understanding Log Formats and Workflow of the Project | MUST HAVE | No Dependency | Gogula Avinash | 3- Completed
S3 | S3 | US-001 | Setting Up the project Environment | MUST HAVE | GitHub,VScode | Gogula Avinash | 3- Completed
S4 | S4 | US-001 | Understanding and Handling about the conflict files in the project | SHOULD HAVE | No Dependency | Gogula Avinash | 3- Completed
S5 | S5 | US-001 | Rectifying the Virtual Environment Errors | SHOULD HAVE | VScode | Gogula Avinash | 3- Completed
S6 | S6 | US-001 | Discussed about JSON files and MetaData | MUST HAVE | No Dependency | Gogula Avinash | 3- Completed
S7 | S7 | US-001 | MileStone 1: Log Processing , Ingestion and project Milestone 1 Overview completed | MUST HAVE | GitHub, VScode | Gogula Avinash | 3- Completed
S8 | S8 | US-001 | Implementation of Log Ingestion Pipeline | MUST HAVE | VScode | Gogula Avinash | 3- Completed
S9 | S9 | US-001 | Log Parsing , Loading data into dask Dataframe , Data validation and cleaning, Distributed engine | MUST HAVE | No Dependency | Gogula Avinash Gogula Avinash Gogula Avinash | 3- Completed
S10 | S10 | US-001 | Milestone2: Submitted the document | SHOULD HAVE | No Dependency | Gogula Avinash | 3- Completed
S11 | S11 | US-001 | Z-Score Anomaly Detection | MUST HAVE | VScode | Gogula Avinash | 3- Completed
S12 | S12 | US-001 | Discussed about the Timestamp | SHOULD HAVE | No Dependency | Gogula Avinash | 3- Completed
S13 | S13 | US-001 | Explored about the SMTP and Statis codes | SHOULD HAVE | No Dependency | Gogula Avinash | 3- Completed
S14 | S14 | US-001 | Email Connection and Email alerts | MUST HAVE | Email,VScode | Gogula Avinash | 2- In Progress
S15 | S15 | US-001 | Streamlit and Streamlit Dashboard | MUST HAVE | No Dependency | Gogula Avinash | 2- In Progress
S16 | S16 | US-001 | Milestone3 : Detection of Anomalies | SHOULD HAVE | No Dependency | Gogula Avinash | 2- In Progress
S17 | S17 | US-001 | Modification of Bargraphs | SHOULD HAVE | Data Visualization | Gogula Avinash | 2- In Progress
S18 | S18 | US-001 | Discussed and worked on Plotly and Streamlit | SHOULD HAVE | Streamlit, Plotly | Gogula Avinash | 2- In Progress
S19 | S19 | US-001 | Explanation of each and every line of a code in a project | MUST HAVE | VScode | Gogula Avinash | 3- Completed
S20 | S20 | US-001 | Dask Dashboard and Streamlit Dashboard | MUST HAVE | Streamlit | Gogula Avinash | 2- In Progress
S21 | S21 | US-001 | Milestone4: Data Visualization , Dashboards , Bargraphs | MUST HAVE | Data Visualization | Gogula Avinash | 2- In Progress
S22 | S22 | US-001 | Running the main.py and app.py files for the final results | MUST HAVE | VScode | Gogula Avinash | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7